## Use Cases data
CBO Unit CBO 1.x | ISU / Vertical | Account | Total Volume (Tickets/Alerts) for the account / month | MFDM Lever / Technology | Implementation Owner | Tower | Source / Work Driver | End to End / Partial | Use Case Name | Use Case Status | Planned Start Date | Planned Design Start Date | Planned Development Start Date | Planned Testing Start Date | Planned Completion Date | Planned Go-Live Date | Actual Start Date | Actual Completion Date | Actual Go-Live Date | KPI Impacted / Business Benefits | Volume Received / month | Volume Resolved / month | Month / Year | FTE Saves for month | Remarks (Reason for Delay /Other Challenges)
CBO 1.3 | Travel and Hospitality | International Airlines Group (IAG) | Sprint 1 | Ansible | Piyush Sinha | Data Centre (DC) | Other | End to End | BA Infrastructure Automation | Completed | 2022-04-04 | 2022-04-04 | 2022-04-04 | 19/4/2022 | 2022-04-05 | 2022-09-30 | 2022-04-04 | 2022-07-11 | Not yet | User Experience | Planned Development | N.A. |  | Fixed Bid - 2 FTE | On Premise Cloud Dev Environment was not working which required Java code fix which took long due to Resource unavailability in the beginning.
CBO 1.3 | Travel and Hospitality | International Airlines Group (IAG) | Sprint 2 | Ansible | Piyush Sinha | Application | Other | End to End | BA Infrastructure Automation | Development | 2022-05-04 | 2022-05-06 | 2022-05-09 | 2022-05-20 | 2022-05-26 | 2022-09-30 | 2022-05-04 | TBD | Not yet | User Experience | Planned Development | N.A. |  | Fixed Bid - 2 FTE | No Chalenges till now for Sprint 2
CBO 1.3 | Travel and Hospitality | Royal Carribean Group (RCG) | 6 | Ansible | Piyush Sinha | Data Centre (DC) | Other | End to End | BA Infrastructure Automation | Development | 2022-04-04 | 2022-04-04 | 2022-04-04 | 19/4/2022 | 2022-04-05 | Not yet planned | 2022-04-04 | TBD | 2022-08-26 | Business Benefit | 6 | 1 |  |  | Awaited timely input from Customer, [weak workforce management at client's end].

## Data Values
MFDM Lever / Technology | Tower | Source / Work Driver | KPI Impacted / Business Benefits | Use Case Status
Ansible | Data Centre (DC) | Alerts | MTTR Reduction | To be Started
ServiceNow | End User Computing (EUC) | Calls | Reduction in Human Error | Discovery
SPLUNK | Middleware | Chats | Server Downtime Reduction | Design
Powershell | Network | User Emails (SD) | Improved Time to Market | Development
Python | Security | Batch Jobs | Effort Reduction | Testing
SCORCH | Service Desk (SD) | HealthCheck | Major Incidents Reduction | Completed
Automation Anywhere | Database | Reports | ROI Improved | Live
UiPath | Application | Dashboard | Noise Reduction | Support
|  | Scheduler | Contacts Reduction | On Hold
|  | Service Requests | Ticket Reduction | Waiting Approval
|  | Incidents | AHT Reduction
|  | Change Requests | Business Benefit
|  | Problem Tickets | User Experience
|  | Other | Other Benefits(Please specify)