## Sheet1
Ticket Category	Wave	Complexity [L/M/H]		Ticket Category	Wave	Complexity [L/M/H]
Software - SCCM ( System Centre deployment)	W2			Software - SCCM ( System Centre Uninstall)	W3
Unable to Login	W1			DL Modification	W5
SAP Issue (Installation Issue)	W5			Hamburg Süd Application Access	W4
Server/URL inaccessible	W1			AVD Application Access Request	W2
Software - Install (Other App.)	W2			Intune Application Request	W6
Password reset/expired	W1			VPN Access Request	W1
MyHR Incident	W3
Distribution List Add/Remove	W5
Distribution Group - Modification	W3
Software - SCCM ( System Centre deployment)	W2
Password Reset Request	W1
IMAC Desktop / Laptop Install (Auto Routing)	W3
Citrix Applications Access	W3
software -GCSS Installation Request	W2
SAP BI Access Request	W3
Hardware Service Request (Auto Routing)	W3
Software - SCCM ( System Centre Upgrade)	W2
Software - Install (Other App.)	W3
Access To Application ( Installation of Other than catalogue Application Deployment )	W4
Software - IP Communicator Install	W2
APMM Console Access Request (Auto Routing)	W4
Domain Password Reset Request	W1
Software - O365 Install	W1
ADM (VM) Account Termination	W3
Software - SCCM ( System Centre Uninstall)	W2
DL Modification	W4
Hamburg Süd Application Access	W4
AVD Application Access Request	W4
Intune Application Request	W4
VPN Access Request	W5
Active Directory Account Lock	W4
Deactivate account - Offboarding	W4
Software - Intune AVD Install	W5
Software - Java Install	W1
Software - Power BI Server Install	W5
Software - Power BI Install	W5
Software - O365 Add-in Access	W5
Power BI Access Request	W5
Quality Analysis Reporting	W2
Reporting	W1

## Sheet2
Task Owner	Task Name	Months
	General Tasks	M1	M2	M3	M4	M5	M6	M7	M8	M9	M10	M11	M12
TCS	Resource Onboarding and Access Requests
APMM	Access management for resources
TCS & APMM	Validate the environment, process, tools and stakeholders
TCS & APMM	Understand current issues/gaps with Automation
TCS	Design the MFDM™ architecture, Identify test environment and access required
APMM	Milestone 1: Agreement and Sign Off on design post ARB and SRB approval	*
TCS & APMM	Understand feasibility of Identified Use cases
TCS & APMM	Prepare a detailed Sprint plan with prioritization and dependencies.
	Discovery
APMM	Provide the SOP and as-is documentation of Identified Use cases
TCS	Discovery of the Use cases and documentation of Identified AS IS process (wave of 8 use cases)
TCS	Milestone 2: Complete Playbook sessins		*	*	*	*	*	*
	Iterative Design / Unit testing Sprint
TCS	Design to be flow for the waves of Use cases
TCS & APMM	Agreement on to be flow with Stakeholders
APMM	Milestone 3: Agreement and Sign Off on detailed to be flow document			*	*	*	*	*	*
	Development and Testing Sprint
TCS & APMM	Setup tha Lab with all tools, Integrations and test environments for the overall program use case
TCS	Milestone 4: Setup of MFDM™ platform for automation
TCS	Develop the 46 use cases in wave of 8 Ucs
TCS	System Testing of 46 use cases
TCS	Develop Test plan for 46 use cases
TCS	Release of the 46 Use cases for UAT
TCS	Bug fixing and Retesting
TCS & APMM	Milestone 5: Final Sign Off on UAT				*	*	*	*	*	*
	Deployment
TCS	Milestone 6: Use cases LIVE - Limited Rollout in Waves					*	*	*	*	*	*
TCS	Rollout and monitor and measure KPI's on the use case
TCS	Milestone 7: Full Rollout and Sign off on Use cases in Waves						*	*	*	*	*	*
TCS	Milestone 8: Completion of Hypercare Support						*