## Slide 1
WEEKLY STATUS REPORT
~ CBO 1.3
05/08/2022

## Slide 2: RCG
Use Case – Phase wise Details for Current Quarter
ISU | Tech Stack | Total use cases | Total ROI Committed | Delivered use cases in FY22 | ROI for Delivered use cases | FY 23 Planned |  |  |  | ROI for the current quarter | Total Coverage | Efficiency | Automation Index | RAG
 |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |  |  |  |  | 
TTH | Ansible, Python, PowerShell |  | 100 | 8 | 0.66 | 5 | 4 | 3 | 2 | 0 | 70% | 60% | 30% | 
Use Cases | To be started / Started | Feasibility PDate | Discovery PDate | Design PDate | Development PDate | Test PDate | Ready for Prod PDate | Live PDate | On-Hold | Challenge if delay
Citrix Cloud Reboot Automation | Yes | 14th July, 22 | 18th July, 22 | 29th July, 22 | 3rd Aug 22  | 19th Aug, 22 | 24th Aug, 22 | 26th Aug, 22 | Yes | Awaiting API credentials from Business
Wireless certificate renewal | Yes | 15th July, 22 | 18th July, 22 | 26th Aug, 22 | 28th Sep, 22 | 30th Sep, 22 | 10th Oct, 22 | 14th Oct, 22 | Yes | Pending with Access from Account Team
SQL version upgrade | Yes | 18th July, 22 | 19th July, 22 | 29th July, 22 | 3rd Aug 22  | 8th Aug, 22 | 24th Aug, 22 | 31st Aug, 22 | Yes | Awaiting test server access.
Windows patching pre-post checks | Yes | 11th July, 22 | 12th July, 22 | 29th Aug, 22 | 7th Sep, 22 | 19th Sep, 22 | 4th Oct, 22 | 7th Oct, 22 | No | No
Mksysb backup report(AIX) | Yes | 11th July, 22 | 12th July, 22 | 13th July, 22 | 14th July, 22 | 5th Aug, 22 | 10th Aug, 22 | 12th Aug, 22 | No | No
PAM integration for credentials fetching | Yes | 11th July, 22 | 13th July, 22 | 29th Aug, 22 | 7th Sep, 22 | 19th Sep, 22 | 4th Oct, 22 | 7th Oct, 22 | Yes | Awaiting PAM credentials from Business
Cylance protect removal process automation request | Yes | 20th July, 22 | 21st July, 22 | 22nd July, 22 | 25th July, 22 | 2nd Aug, 22 | 10th Aug, 22 | 12th Aug, 22 | No | No
Delivery Highlights
Delivery Issues
Issues | Actions/Resolutions | Owner | ETR
Synch is not accurate between the PagerDuty and ServiceNow and causes data mismatch. | Weak workforce management, Analysis In progress for better resolution | RCG | 30th Dec, 2022
Low responsiveness at RCG, we are unable to get the basic requirement fulfilled on time like test server availability, access management, etc. | Onsite is working to resolve this ASAP. | Account Team | 30th Sep, 2022
Total 7 on going use cases started in Q2,FY’23. 4 use cases are expected to be delivered in Q2.
Target Plan for 10-12 use cases FY’ 2023. Working aggressively with Vertical Leads and Business to materialize more automation work. ETA : Q3, FY’23.
About : RCG is a global cruise holding company incorporated in Liberia and based in Miami, Florida, US. It is the world's second-largest cruise line operator. Volumetrics : 10,000 servers, 1300 network devices, 10 applications, 52 locations/data centres, 2680 requests/month, 15456 incidents/month, 505 CR/month. Scope : 9 servers, 2 locations/data centres

## Slide 3: IAG
Use Case – Phase wise Details for Current Quarter
ISU | Tech stack | Total Integrations / Jobs | Total ROI Committed | Delivered Jobs in FY22 | ROI for Delivered Jobs / Integration | FY 23 Planned |  |  |  | ROI for the current quarter | Total Coverage | Efficiency | Automation Index | RAG
 |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |  |  |  |  | 
TTH | Ansible, Python, Jenkins | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 |  |  |  | 
Delivery Highlights
Delivery Issues
Issues | Actions/Resolutions | Owner | ETR
Project is delayed by 1 month due to Java Spring boot resource crunch and DEV environment issues at early stage. Tentative Go-LIVE is now pushed to first week of September. | Onboarded [05/08/2022] | Account Team | 30th Sep, 2022
Project is running 1 month delay :
Sprint 1 completed on 4th July [a month delay] and Sprint 2 is in progress with target date as 5th of August.
Project final Sprint 3 is expected to complete between 04 – 09 September.
Project expected to be closed by September mid [tentative].
2. Past Sprint Activities (sprint 1): [Completed]
Environmental setup and several code configurations.
3. Upcoming Sprint Activities (Sprint 3): [To be started]
On premise UI and DB changes with several integrations and Testing.
Integrations / Job Name | To be started / Started | Feasibility PDate | Discovery PDate | Design PDate | Development PDate | Test PDate | Ready for Prod PDate | Live PDate | On-Hold | Challenge if delay
Post configuration [Ansible Tower] Ansible codes creation | Yes | 13th July, 22 | 13th July, 22 | 14th July, 22 | 14th July, 22 | 22nd Aug, 22 | 26th Aug, 22 | 30th Sep, 22 | No | No
API development for integrating Ansible Tower with On-Premise Cloud Application. | Yes | 12th July, 22 | 13th July, 22 | 14th July, 22 | 14th July, 22  | 22nd Aug, 22 | 26th Aug, 22 | 30th Sep, 22 | No | No
Dev Environment build and deployment check using Jenkins | Yes | 12th July, 22 | 13th July, 22 | 14th July, 22 | 14th July, 22  | 22nd Aug, 22 | 26th Aug, 22 | 30th Sep, 22 | No | No
RHEL 8 changes for on-premise RIP cloud Application | Yes | 12th July, 22 | 13th July, 22 | 14th July, 22 | 14th July, 22 | 22nd Aug, 22 | 26th Aug, 22 | 30th Sep, 22 | No | No
About : IAG is one of the world's largest airline groups, with a fleet of 531 aircraft. Before the impact of the COVID-19 pandemic it operated to 279 destinations and carried around 118 million passengers each year. It is a Spanish registered company with shares traded on the London Stock Exchange and Spanish Stock Exchanges. Volumetrics : 11 servers, 1300 network devices, 40 applications, 52 locations/data centres, 2680 requests/month, 15456 incidents/month, 505 CR/month. Scope :

## Slide 4
Overall Accounts Score/Progress Report (TTH)
Accounts Health and if Risks
Delivery Highlights: Delta Account Ansible Automation to start – [in pipeline]. Expecting billing start very soon. 2 positions [Most Likely - ML] might open after Account discussion with our Ansible Automation Team. 8 use cases have been completed and successfully delivered till Date for RCG. IAG is all on track and Sprint 2 completion expected by 26th Aug, 2022. Project completion by 30th Sep, 2022. Total Strength ¦ Hours saved ¦ Efficiency ¦ Automation Index: RCG=4, IAG=3 Hours Saved = 60 in 3 months, 20 / month Efficiency = 60% Automation Index = 30% Risk Details: 1-2 positions are not fulfilling for RCG as Low responsiveness and setup which itself is not even 80% completed at their end. Delay in Contract renewal is causing revenue impact for IAG. 3 FTE Non-Billable for Aug, 2022. No. of positions at risk (Account wise): – RCG – 2. Delivery impact on subsequent projects, Total positions at risk: 2 Mitigation/Action Plan: Onsite [Account team] is working to resolve the use cases risk for RCG. Hiring Status: Positions Open – 6 Sourcing WIP – 2 Interview in progress – 0 Virtual Drives planned – 0
Chart: No. of Total Open Positions
| BL | ML | Upside
No. of Positions | 5 | 1 | 0
Chart: Open Positions Account Wise
| RCG | Delta | IAG
No. of Positions | 1 | 3 | 2