## Slide 1
WEEKLY STATUS REPORT
~ CBO 1.3
31/08/2022

## Slide 2: EAAP KPI Measurement for CBO 1.3
In Scope for EAAP
B: 700
C: 100
Eliminated
D: 0
Enriched as per design
F: 350
Fully Automated
Total Incidents/ SR/Changes/Alerts/
Contacts in Account
A: 8411
EAAP Coverage: Total # of Tickets Covered till date (G)
Total # of tickets to EAAP (B)
=
71%
EAAP Effectiveness: # Tickets resolved as per design (C+D+F)
# Tickets covered till Date (G)
=
90%
E: 50
Failed
EAAP Automation Index (AI): # Tickets fully automated (F)
Total # of tickets to EAAP (B)
=
50%
Total # of Tickets Covered till date (G): C+D+E+F = 500
Index | Q1 | Q2 | Q3 | Q4
EAAP Coverage |  | 71% |  | 
EAAP Effectiveness |  | 90% |  | 
EAAP AI |  | 50% |  | 

## Slide 3
ISU | Tech Stack | Total Tickets (A) | Total tickets in scope (B) | Total Effort in hours/month | Total use cases | UC Delivered in FY22 | FY 23 Planned/delivered use cases |  |  |  | Total Tickets automated till date (G) | Effort automated (hours/month) | Tickets resolved + Eliminated as per design ( D) | Total E2E resolved tickets (F) | Total Coverage (G/B) % | Efficiency (D/G)% | Automation Index (F/B)% | Status
 |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |  |  |  |  |  |  |  | 
TTH | Ansible, Python, PowerShell | 8411 | 700 | 160 | 20 | 8 | 5 | 4 | 3 | 0 | 550 | 140 | 80 | 350 | 79% | 96% | 50% | 
Use Cases for current Quarter | To be started / Started | Feasibility PDate | Discovery PDate | Design PDate | Development PDate | Test PDate | Ready for Prod PDate | Live PDate | On-Hold | Challenge if delay
Citrix Cloud Reboot Automation | Yes | 14th July, 22 | 18th July, 22 | 29th July, 22 | 3rd Aug 22  | 19th Aug, 22 | 2nd Sep, 22  | 21st Sep, 22 | No | Development started this week as dependencies not met on time.
Wireless certificate renewal | Yes | 15th July, 22 | 18th July, 22 | 26th Aug, 22 | 28th Sep, 22 | 30th Sep, 22 | 10th Oct, 22 | 14th Oct, 22 | Yes | API which they have given is not allowing certificate download. Working on it.
SQL version upgrade | Yes | 18th July, 22 | 19th July, 22 | 29th July, 22 | 3rd Aug 22  | 8th Aug, 22  | 24th Aug, 22  | 12st Sep, 22 | No | Development started late (13 Aug) due to dependencies not met on time.
Windows patching pre-post checks | Yes | 11th July, 22 | 12th July, 22 | 29th Aug, 22 | 7th Sep, 22 | 19th Sep, 22 | 4th Oct, 22 | 7th Oct, 22 | No | No
Mksysb backup report(AIX) | Yes | 11th July, 22 | 12th July, 22 | 13th July, 22 | 14th July, 22 | 5th Aug, 22 | 10th Aug, 22 | 12th Sep, 22 | No | No
PAM integration for credentials fetching | Yes | 11th July, 22 | 13th July, 22 | 29th Aug, 22 | 7th Sep, 22 | 19th Sep, 22 | 4th Oct, 22 | 7th Oct, 22 | No | No
Cylance protect removal process automation request | Yes | 20th July, 22 | 21st July, 22 | 22nd July, 22 | 25th July, 22 | 2nd Aug, 22 | 10th Aug, 22 | 12th Sep, 22 | No | No
Category | Description | Actions/Resolutions | Owner | ETR
Issue | Synch is not accurate between the PagerDuty and ServiceNow and causes data mismatch. | Weak workforce management, Analysis In progress for better resolution | RCG | 30th Dec, 2022
Risk | Low responsiveness at RCG, we are unable to get the basic requirement fulfilled on time like test server availability, access management, etc. | Onsite co-ordinator is working to resolve this ASAP. | Account Team | 30th Sep, 2022
About : RCG is a global cruise holding company incorporated in Liberia and based in Miami, Florida, US. It is the world's second-largest cruise line operator. Volumetrics : 10,000 servers, 1300 network devices, 10 applications, 52 locations/data centres, 3313 requests/month, 2418 incidents/month, 2680 CR/month. Scope : 52 servers, 40 network devices, 3 locations/data centres, 250 requests/month, 400 incidents/month, 50 CR/month Contractual Automation Commitment as per SOW :

## Slide 4
ISU | Tech Stack | Total Tickets (A) | Total tickets in scope (B) | Total Effort in hours/month | Total use cases | Delivered in FY22 | FY 23 Planned/delivered Integrations/Jobs |  |  |  | Total Tickets automated till date (G) | Effort automated (hours/month) | Tickets resolved + Eliminated as per design ( D) | Total E2E resolved tickets (F) | Total Coverage (G/B) % | Efficiency (D/G)% | Automation Index (F/B)% | Status
 |  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |  |  |  |  |  |  |  | 
TTH | Ansible, Python | NA | NA | Fixed | NA | 0 | 3 | 4 | 0 | 0 | NA | NA | NA | NA | 40% | 60% | 30% | 
Integrations for current quarter | To be started / Started | Feasibility PDate | Discovery Pdate | Design PDate | Development PDate | Test PDate | Ready for Prod PDate | Live PDate | On-Hold | Challenge if delay
Post configuration [Ansible Tower] Ansible codes creation | Yes | 13th July, 22 | 13th July, 22 | 14th July, 22 | 14th July, 22 | 22nd Aug, 22 | 26th Aug, 22 | 30th Sep, 22 | No | No
API development for integrating Ansible Tower with On-Premise Cloud Application. | Yes | 12th July, 22 | 13th July, 22 | 14th July, 22 | 14th July, 22 | 22nd Aug, 22 | 26th Aug, 22  | 30th Sep, 22 | No | No
Dev Environment build and deployment check using Jenkins | Yes | 12th July, 22 | 13th July, 22 | 14th July, 22 | 14th July, 22 | 22nd Aug, 22 | 26th Aug, 22 | 30th Sep, 22 | No | No
RHEL 8 changes for on-premise RIP cloud Application | Yes | 12th July, 22 | 13th July, 22 | 14th July, 22 | 14th July, 22 | 22nd Aug, 22 | 26th Aug, 22 | 30th Sep, 22 | No | No
Third party tool Installation for RHEL 8 – 5 count | Yes | 2nd Sep, 22 | 6th Sep, 22 | 9th Sep, 22 | 12th Sep, 22 | 22nd Sep, 22 | 26th Sep, 22 | 30th Sep, 22 | No | No
About : IAG is one of the world's largest airline groups, with a fleet of 531 aircraft. Before the impact of the COVID-19 pandemic it operated to 279 destinations and carried around 118 million passengers each year. It is a Spanish registered company with shares traded on the London Stock Exchange and Spanish Stock Exchanges. Volumetrics : 8000+ servers, 1300 network devices, 10 applications, 3 locations/data centres Scope : 600 servers, 2 locations/data centres, 1 Application Contractual Automation Commitment as per SOW : Fixed Bid [2 FTE – 4 months]
Category | Description | Actions/Resolutions | Owner | ETR
Appreciation | Customer appreciated the on-time delivery for sprint 1 and 2. | NA | NA | NA

## Slide 5
Overall TTH Highlights and Support required
Account | Open Positions | Skill | Experience needed | Billable/Non-Billable | Remarks
Delta | 3 (tentative) | Ansible | TBD | Billable | Yet to be discussed for Ansible scope.
Delivery Highlights
Sprint 2 for IAG Account completes on 26th August. Everything is on track and GO-LIVE planned by Oct, 2nd week tentatively.
RCG is moving under Account team’s scope as no further visibility seen from Ansible perspective.
Delta Account Automation discussions have to be started once Account team shares the meeting slot.
Maersk Proposal is in discussion and Automation Plan for 46 use cases have been shared for 10 months with the Account team. Awaiting internal review completion post which the Plan will be shared with Customer. ETA by 2nd Sep, 2022.
Support required from IA