## Pre-requisites
Sl# | Activity | Owner | Status | Planned End Date | Actual End Date
1 | Discussion with Unix and Wintel Tower for Use case prioritization | Account Team | Completed | 2022-08-11 | 2022-08-11
2 | Provide Pre-requisites for AWX Installation | MFDM Team | Open | 2022-08-12 | 2022-08-12
3 | Ansible CLI access - On Prem and Cloud | Account Team | Open | 2022-08-17
4 | Ansible AWX Installation - On Prem | MFDM/Unix/Wintel | Open | 2022-08-17 |  | Most Important pre-requisites/pre-conditions
5 | Ansible AWX Access on Cloud | Account Team | Open | 2022-08-17
6 | SOP/Documentation with all the Manual steps detailed | UNIX/Wintel tower | Open | 2022-08-17 |  | 1. The servers should be able to connect to Internet and reach sites like GitLab, GitHub, Ansible Galaxy, Google, etc. 2. We should be able to download software and install them, i.e. have admin rights. 3. Google Chrome and Medge should be installed. 4. Pre-requisites for the AWX installation should be provided.
7 | Service Account readiness for both Linux and Windows | UNIX/Wintel tower | Open | 2022-08-17
8 | Resource Onboarding and Account creation with proper access(praveen and Selva) | Account Team | Open | 2022-08-17
9 | Test Environment for LINUX/AIX | UNIX | Open | 2022-08-17
10 | Test Environment for Windows | Wintel tower | Open | 2022-08-17
11 | Account specific GitLab Access (praveen and Selva) | Account Team | Open | 2022-08-17
12 | Account specific ServiceNow access with proper privilege (Non PROD) | Account Team | Open | 2022-08-18
13 | ServiceNow Mid Server installation (LINUX variant) on Ansible Server | Account Team/MFDM Team | Open | 2022-08-18

## Master Data - Use Cases
Release 1.0
Sl# | Use Cases List | Feasibility and Pre-requisites | Discovery Phase |  | Design Phase |  | Development Phase |  | Deployment Phase [PROD] |  | RAG
|  |  | Planned Start | Planned End | Planned Start | Planned End | Planned Start | Planned End | Planned Start | Planned End
1 | High Resource utilization (Linux) 1.a CPU/Memory 1.b FileSystem 1.c Paging |  | 2022-08-11 | 2022-08-18 | 2022-08-19 | 2022-08-21 | 2022-08-22 | 2022-08-31 | 2022-09-01 | 2022-09-03
2 | High Resource utilization (Windows) 2.a CPU/Memory 2.b FileSystem 2.c Paging |  | 2022-08-11 | 2022-08-18 | 2022-08-19 | 2022-08-21 | 2022-08-22 | 2022-08-31 | 2022-09-01 | 2022-09-03
3 | Node Down status (Linux) |  | 2022-08-11 | 2022-08-18 | 2022-08-19 | 2022-08-21 | 2022-08-22 | 2022-08-31 | 2022-09-01 | 2022-09-03
4 | Node Down status (Windows) |  | 2022-08-11 | 2022-08-18 | 2022-08-19 | 2022-08-21 | 2022-08-22 | 2022-08-31 | 2022-09-01 | 2022-09-03

## High Resource Utilization
Sl# | Activity | Task Dependency [If any] | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Comments
1 | Creation of inventory file on the master node. Adding all the target nodes/devices as Ansible inventory. |  | 2022-08-22 | 2022-08-23 |  |  | Initialization
2 | Establish the Connectivity with target nodes/devices |  | 2022-08-23 | 2022-08-23 |  |  | Initialization
3 | ServiceNow Mid Server Installation on Ansible Server |  | 2022-08-24 | 2022-08-24 |  |  | Initialization
4 | Integration of Servicenow with Ansible AWX |  | 2022-08-24 | 2022-08-24 |  |  | Initialization
Milestone 1
5 | Design of Blueprint for the Identified UC |  | 2022-08-25 | 2022-08-26 |  |  | Initialization
6 | Functional Walk through of the Blue print and Sign-Off |  | 2022-08-26 | 2022-08-26 |  |  | Initialization
7 | Development of approved Blue print of UC |  | 2022-08-27 | 2022-08-30 |  |  | Initialization
8 | Demo Session of the developed UC in Dev/Test Env. |  | 2022-08-31 | 2022-08-31 |  |  | Initialization | Will be planned in the Second half
9 | UAT Sign-Off |  | 2022-08-31 | 2022-08-31 |  |  | Initialization
Milestone 2
10 | CR Approval for Prod Deployment |  | 2022-09-01 | 2022-09-02 |  |  | Initialization
11 | Deploy this UC into the PROD all target Servers |  | 2022-09-02 | 2022-09-04 |  |  | Initialization
12 | Smoke Testing on Prod |  | 2022-09-05 | 2022-09-06 |  |  | Initialization | This will be perfomed on some random servers.
13 | Prod Sign-Off |  | 2022-09-06 | 2022-09-08 |  |  | Initialization

## Node Down status
Sl# | Activity | Task Dependency [If any] | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Comments
1 | Creation of inventory file on the master node. Adding all the target nodes/devices as Ansible inventory. |  | 2022-08-22 | 2022-08-23 |  |  | Initialization
2 | Establish the Connectivity with target nodes/devices |  | 2022-08-23 | 2022-08-23 |  |  | Initialization
3 | ServiceNow Mid Server Installation on Ansible Server |  | 2022-08-24 | 2022-08-24 |  |  | Initialization
4 | Integration of Servicenow with Ansible AWX |  | 2022-08-24 | 2022-08-24 |  |  | Initialization
Milestone 1
5 | Design of Blueprint for the Identified UC |  | 2022-08-25 | 2022-08-26 |  |  | Initialization
6 | Functional Walk through of the Blue print and Sign-Off |  | 2022-08-26 | 2022-08-26 |  |  | Initialization
7 | Development of approved Blue print of UC |  | 2022-08-27 | 2022-08-30 |  |  | Initialization
8 | Demo Session of the developed UC in Dev/Test Env. |  | 2022-08-31 | 2022-08-31 |  |  | Initialization | Will be planned in the Second half
9 | UAT Sign-Off |  | 2022-08-31 | 2022-08-31 |  |  | Initialization
Milestone 2
10 | CR Approval for Prod Deployment |  | 2022-09-01 | 2022-09-02 |  |  | Initialization
11 | Deploy this UC into the PROD all target Servers |  | 2022-09-02 | 2022-09-04 |  |  | Initialization
12 | Smoke Testing on Prod |  | 2022-09-05 | 2022-09-06 |  |  | Initialization | This will be perfomed on some random servers.
13 | Prod Sign-Off |  | 2022-09-06 | 2022-09-08 |  |  | Initialization

## Issues
Error | Fix | Remarks